## WBS
Task name | Dependencies | BA | UI/UX | Dev Team lead | Dev Ops | BE | System / DB architect | FE | Technical writer | QA | PM | Total
Total (hours) |  | 327 | 364 | 544 | 84 | 1223.4 | 120 | 617.8 | 108 | 501.04 | 972.31 | 4861.55
1 Generic activities
1.1 Set up development environment |  |  |  |  | 24
1.2 Set up version control system (Git) |  |  |  |  | 8
1.3 Set up CI / CD processes |  |  |  |  | 16
1.4 Set up monitoring and logging system |  |  |  |  | 16
1.5 Design system / DB architectures | [6 empty] | 24
1.6 Select technology stack |  |  |  | 8
2 Project and user management
2.1 Gather and document requirements from stakeholders |  | 16
2.2 Prepare user stories and software requirement specification | 2.1 | 24
2.3 Create wareframes and prototypes | 2.2 |  | 20
2.4 Create key UI/UX design modules | 2.3 |  | 32
2.5 Design architecture | 1.5, 1.6 |  |  | 24
2.6 Interaction protocols | 1, 2.3, 2.4, 2.5 |  |  |  |  | 8 |  | 8
2.7 Create and edit projects
2.7.1 Project creation form | 1.1, 1.2, 1.3, 1.4, 2.3, 2.4 | [6 empty] | 12
2.7.2 Project editing functionality | 1.1, 1.2, 1.3, 1.4, 2.3, 2.4 | [6 empty] | 16
2.7.3 Create database models | 2.5 | [5 empty] | 16
2.7.4 Implement data relationships | 1.1, 1.2, 1.3, 1.4, 2.5 |  |  |  |  | 20
2.7.5 Implement CRUD operations | 1.1, 1.2, 1.3, 1.4, 2.5 |  |  |  |  | 24
2.7.6 Develop API | 2.6 |  |  |  |  | 8
2.8 Manage Employee Information
2.8.1 Employee registration form | 1.1, 1.2, 1.3, 1.4, 2.3, 2.4 | [6 empty] | 12
2.8.2 Employee profile management | 1.1, 1.2, 1.3, 1.4, 2.3, 2.4 | [6 empty] | 16
2.8.3 Employee role management | 1.1, 1.2, 1.3, 1.4, 2.3, 2.4 | [6 empty] | 16
2.8.4 Create database models | 2.5 | [5 empty] | 16
2.8.5 Implement data relationships | 1.1, 1.2, 1.3, 1.4, 2.5 |  |  |  |  | 20
2.8.6 Implement CRUD operations | 1.1, 1.2, 1.3, 1.4, 2.5 |  |  |  |  | 24
2.8.7 Develop API | 2.6 |  |  |  |  | 8
2.9 Assistance and code review |  |  |  | 16
2.10 Stabilization | 2.7, 2.8 |  |  | 12 |  | 33.6 |  | 24
2.11 Release preparation
2.11.1 Prepare release notes | 2.10 |  |  | 8
2.11.2. Set up CI / CD processes | 2.10 |  |  |  | 4
2.11.3 Coordinate release activities |  |  |  | 16
2.12 RELEASE "Project and user management"
2.12.1 Demo Release "Project and user management" | 2.11 | 2
2.12.2 Release & demo results analysis | 2.12.1 | 8
2.12.3 Release & demo improvements planning | 2.12.2 |  |  | 12
3 Task management
3.1 Gather and document requirements from stakeholders |  | 16
3.2 Prepare user stories and software requirement specification | 3.1 | 24
3.3 Create wareframes and prototypes | 3.2 |  | 20
3.4 Create key UI/UX design modules | 3.3 |  | 32
3.5 Design architecture | 1.5, 1.6 |  |  | 24
3.6 Interaction protocols | 1, 3.3, 3.4, 3.5 |  |  |  |  | 8 |  | 8
3.7 Create and edit tasks with detailed information
3.7.1 Task creation form | 2.7, 3.3, 3.4 | [6 empty] | 12
3.7.2 Task editing functionality | 2.7, 3.3, 3.4 | [6 empty] | 16
3.7.3 Detailed task information fields | 2.7, 3.3, 3.4 | [6 empty] | 16
3.7.4 Create database models | 3.5 | [5 empty] | 16
3.7.5 Implement data relationships | 2.7, 3.5 |  |  |  |  | 20
3.7.6 Implement CRUD operations | 2.7, 3.5 |  |  |  |  | 24
3.7.7 Develop API | 3.6 |  |  |  |  | 8
3.8 Assign employees to projects and tasks
3.8.1 Assignment interface | 2.8, 3.3, 3.4, 3.7 | [6 empty] | 12
3.8.2 Assignment logic | 2.8, 3.5, 3.7 |  |  |  |  | 20
3.8.3 Project / Task employee list | 2.8, 3.3, 3.4, 3.7 | [6 empty] | 16
3.8.4 Create database models | 3.5 | [5 empty] | 16
3.8.5 Implement data relationships | 2.8, 3.5, 3.7 |  |  |  |  | 20
3.8.6 Develop API | 3.6 |  |  |  |  | 8
3.9 Set task deadlines
3.9.1 Deadline input field | 3.7 | [6 empty] | 8
3.9.2 Deadline validation | 3.7 |  |  |  |  | 12
3.9.3 Develop API | 3.6 |  |  |  |  | 4
3.10 Task dependency linking
3.10.1 Dependency selection interface | 3.7 | [6 empty] | 12
3.10.2 Dependency logic | 3.7 |  |  |  |  | 20
3.10.3 Develop API | 3.6 |  |  |  |  | 4
3.11 Ability to add multiple assignees to a task
3.11.1 Multiple assignee selection | 2.8, 3.7 | [6 empty] | 12
3.11.2 Multiple assignee logic | 2.8, 3.7 |  |  |  |  | 20
3.11.3 Develop API | 3.6 |  |  |  |  | 4
3.12 Search and filter tasks
3.12.1 Search input | 3.8 | [6 empty] | 8
3.12.2 Filter selection | 3.8 | [6 empty] | 12
3.12.3 Search input logic | 3.8 |  |  |  |  | 16
3.12.4 Filter selection logic | 3.8 |  |  |  |  | 16
3.12.5 Develop API | 3.6 |  |  |  |  | 8
3.13 View task history
3.13.1 Task history display | 3.11 | [6 empty] | 16
3.13.2 History tracking logic | 3.11 |  |  |  |  | 20
3.13.3 Develop API | 3.6 |  |  |  |  | 4
3.14 Assistance and code review |  |  |  | 16
3.15 Stabilization | 3.12, 3.13 |  |  | 12 |  | 70.8 |  | 44.4
3.16 Release preparation
3.16.1 Prepare release notes | 3.15 |  |  | 8
3.16.2. Set up CI / CD processes | 3.15 |  |  |  | 4
3.16.3 Coordinate release activities |  |  |  | 16
3.17 RELEASE "Task management"
3.17.1 Demo Release "Task management" | 3.16 | 1
3.17.2 Release & demo results analysis | 3.17.1 | 8
3.17.3 Release & demo improvements planning | 3.17.2 |  |  | 12
4 Progress tracking
4.1 Gather and document requirements from stakeholders |  | 16
4.2 Prepare user stories and software requirement specification | 4.1 | 24
4.3 Create wareframes and prototypes | 4.2 |  | 20
4.4 Create key UI/UX design modules | 4.3 |  | 32
4.5 Design architecture | 1.5, 1.6 |  |  | 24
4.6 Interaction protocols | 1, 4.3, 4.4, 4.5 |  |  |  |  | 8 |  | 8
4.7 Visualize task progress
4.7.1 Progress bar / indicator | 3.9, 4.3, 4.4 | [6 empty] | 12
4.7.2 Progress calculation logic | 3.9, 4.5 |  |  |  |  | 20
4.7.3 Develop API | 4.6 |  |  |  |  | 20
4.8 Track time spent on tasks
4.8.1 Time tracking input | 3.11, 4.3, 4.4 | [6 empty] | 8
4.8.2 Time tracking logic | 3.11, 4.5 |  |  |  |  | 16
4.8.3 Develop API | 4.6 |  |  |  |  | 20
4.9 Assistance and code review |  |  |  | 16
4.10 Stabilization | 4.7, 4.8 |  |  | 6 |  | 12.6 |  | 4.2
5 Communication and notifications
5.1 Gather and document requirements from stakeholders |  | 16
5.2 Prepare user stories and software requirement specification | 5.1 | 24
5.3 Create wareframes and prototypes | 5.2 |  | 20
5.4 Create key UI/UX design modules | 5.3 |  | 32
5.5 Design architecture | 1.5, 1.6 |  |  | 24
5.6 Interaction protocols | 1, 5.3, 5.4, 5.5 |  |  |  |  | 8 |  | 8
5.7 Notifications about task assignments and status changes
5.7.1 Notification display | 3.11, 5.3, 5.4 | [6 empty] | 12
5.7.2 Notification system | 3.11, 5.5 |  |  |  |  | 16
5.7.3 Develop API | 5.6 |  |  |  |  | 20
5.8 Task comments
5.8.1 Comment input and display | 3.7, 5.3, 5.4 | [6 empty] | 12
5.8.2 Develop API | 3.7, 5.5 |  |  |  |  | 20
5.8.3 Comment logic | 5.6 |  |  |  |  | 16
5.9 Internal messaging between employees
5.9.1 Messaging interface | 2.8, 5.3, 5.4 | [6 empty] | 16
5.9.2 Messaging logic | 2.8, 5.5 |  |  |  |  | 20
5.9.3 Develop API | 5.6 |  |  |  |  | 20
5.10 Assistance and code review |  |  |  | 16
5.11 Stabilization | 5.7, 5.8, 5.9 |  |  | 6 |  | 18 |  | 7.2
5.12 Release preparation
5.12.1 Prepare release notes | 5.11 |  |  | 8
5.12.2. Set up CI / CD processes | 5.11 |  |  |  | 4
5.12.3 Coordinate release activities |  |  |  | 16
5.13 RELEASE "Progress tracking, communication and notifications"
5.13.1 Demo Release "Progress tracking, communication and notifications" | 5.12 | 1
5.13.2 Release & demo results analysis | 5.13.1 | 8
5.13.3 Release & demo improvements planning | 5.13.2 |  |  | 12
6 Access control
6.1 Gather and document requirements from stakeholders |  | 16
6.2 Prepare user stories and software requirement specification | 6.1 | 24
6.3 Create wareframes and prototypes | 6.2 |  | 20
6.4 Create key UI/UX design modules | 6.3 |  | 32
6.5 Design architecture | 1.5, 1.6 |  |  | 24
6.6 Interaction protocols | 1, 6.3, 6.4, 6.5 |  |  |  |  | 8 |  | 8
6.7 Access control for projects and tasks
6.7.1 Access control interface | 4, 5, 6.3, 6.4 | [6 empty] | 12
6.7.2 Role-based access control | 4, 5, 6.5 |  |  |  |  | 16
6.7.3 Permission management | 4, 5, 6.5 |  |  |  |  | 20
6.7.4 Develop API | 6.6 |  |  |  |  | 20
6.8 User authentication and authorization
6.8.1 Login functionality | 4, 5, 6.3, 6.4 | [6 empty] | 16
6.8.2 User registration | 4, 5, 6.3, 6.4 | [6 empty] | 16
6.8.3 Session management | 4, 5, 6.5 |  |  |  |  | 20
6.8.4 Create database models | 6.5 | [5 empty] | 16
6.8.5 Implement data relationships | 4, 5, 6.5 |  |  |  |  | 20
6.8.6 Implement CRUD operations | 4, 5, 6.5 |  |  |  |  | 24
6.8.7 Develop API | 6.6 |  |  |  |  | 20
6.9 Assistance and code review |  |  |  | 16
6.10 Stabilization | 6.7, 6.8 |  |  | 8 |  | 29.6 |  | 10.4
6.11 Release preparation
6.11.1 Prepare release notes | 6.10 |  |  | 8
6.11.2. Set up CI / CD processes | 6.10 |  |  |  | 4
6.11.3 Coordinate release activities |  |  |  | 16
6.12 RELEASE "Access control"
6.12.1 Demo Release "Access control" | 6.11 | 1
6.12.2 Release & demo results analysis | 6.12.1 | 8
6.12.3 Release & demo improvements planning | 6.12.2 |  |  | 12
7 Reporting and analytics
7.1 Gather and document requirements from stakeholders |  | 16
7.2 Prepare user stories and software requirement specification | 7.1 | 24
7.3 Create wareframes and prototypes | 7.2 |  | 20
7.4 Create key UI/UX design modules | 7.3 |  | 32
7.5 Design architecture | 1.5, 1.6 |  |  | 24
7.6 Interaction protocols | 1, 7.3, 7.4, 7.5 |  |  |  |  | 8 |  | 8
7.7 Reports on projects and employees
7.7.1 Access control interface | 3, 7.3, 7.4 | [6 empty] | 12
7.7.2 Project status reports | 3, 7.5 |  |  |  |  | 16
7.7.3 Employee workload reports | 3, 7.5 |  |  |  |  | 20
7.7.4 Develop API | 7.6 |  |  |  |  | 20
7.8 Analytics on employee workload
7.8.1 Workload dashboard | 3, 7.3, 7.4 | [6 empty] | 24
7.8.2 Workload analysis algorithms | 3, 7.5 |  |  |  |  | 24
7.8.3 Develop API | 7.6 |  |  |  |  | 20
7.9 Data export in various formats | 7.7, 7.8
7.9.1 Export project data | [5 empty] | 16
7.9.2 Export employee data | [5 empty] | 16
7.9.3 Develop API | 7.6 |  |  |  |  | 20
7.10 Assistance and code review |  |  |  | 16
7.11 Stabilization | 7.7, 7.8 |  |  | 12 |  | 48 |  | 13.2
8 Search and filtering
8.1 Gather and document requirements from stakeholders |  | 16
8.2 Prepare user stories and software requirement specification | 8.1 | 24
8.3 Create wareframes and prototypes | 8.2 |  | 20
8.4 Create key UI/UX design modules | 8.3 |  | 32
8.5 Design architecture | 1.5, 1.6 |  |  | 24
8.6 Interaction protocols | 1, 8.3, 8.4, 8.5 |  |  |  |  | 8 |  | 8
8.7 Advanced search for projects, tasks, and employees
8.7.1 Search by multiple criteria | 4, 8.3, 8.4 | [6 empty] | 20
8.7.2 Search results display | 4, 8.3, 8.4 | [6 empty] | 16
8.7.3 Search by multiple criteria logic | 4, 8.5 |  |  |  |  | 24
8.7.4 Develop API | 8.6 |  |  |  |  | 20
8.8 Task filtering by various criteria
8.8.1 Filter by status, priority, assignee, project | 4, 8.3, 8.4 | [6 empty] | 20
8.8.2 Save and reuse filter presets | 4, 8.3, 8.4 | [6 empty] | 24
8.8.3 Create database models | 8.5 | [5 empty] | 16
8.8.4 Implement data relationships | 4, 8.5 |  |  |  |  | 20
8.8.5 Implement CRUD operations | 4, 8.5 |  |  |  |  | 24
8.8.6 Develop API | 8.6 |  |  |  |  | 20
8.9 Assistance and code review |  |  |  | 16
8.10 Stabilization | 8.7, 8.8 |  |  | 12 |  | 34.8 |  | 26.4
8.11 Release preparation
8.11.1 Prepare release notes | 8.10 |  |  | 8
8.11.2. Set up CI / CD processes | 8.10 |  |  |  | 4
8.11.3 Coordinate release activities |  |  |  | 16
8.12 Final RELEASE
8.12.1 Demo Final Release | 8.11 | 2
8.12.2 Release & demo results analysis | 8.12.1 | 8
8.12.3 Release & demo improvements planning | 8.12.2 |  |  | 12
9 Wrap up activities | 6, 7, 8
9.1 Documentation preparation
9.1.1 Final Report | [8 empty] | 16
9.1.2 Lessons learned | [8 empty] | 12
9.2 Backup / Archive creation
9.2.1 Send copies, manuals to stakeholders |  |  |  | 8
9.2.2 Enrich the knowledge base | [8 empty] | 16
9.3 User feedback analysis
9.3.1 Collect user feedback | [8 empty] | 12
9.3.2 Create summary of insights | [8 empty] | 16
9.4 Creation of user training materials / customer education guidelines
9.4.1 Create user manuals | [8 empty] | 16
9.4.2 Develop training sessions | [8 empty] | 20