## RACI_Darina Ozgun_V1
№ | Project deliverable / Activity | Project manager | Business analyst | UI/UX designer | Dev Tem lead | DevOps engineer | Backend developer | System/DB architect | Frontend developer | QA Team lead | QA engineer | Technical writer
1 | Define project scope | R/A |  |  | C
2 | Identify stakeholders | R/A | I
3 | Communicate with stakeholders | R/A | R | R | R
4 | Create project management plan | R/A
5 | Create communication plan | R/A | I | I | I | I | I | I | I | I | I | I
6 | Create work breakdown structure | R/A | R |  | C
7 | Create project roadmap | R/A | I | I | I | I | I | I | I | I | I | I
8 | Plan resource allocation | R/A |  |  | C |  |  |  |  | C
9 | Risk management | R/A |  |  | C
10 | Monitor project progress and deadlines | R/A
11 | Task assignment | R/A | I | I | R | I | I | I | I | R | I | I
12 | Issue escalation | R/A |  |  | R |  |  |  |  | R
13 | Deffects management | R/A | C | C | C |  | C | C | C | C | C
14 | Requirements gathering |  | R/A
15 | Requirements analysis |  | R/A
16 | Requirements documentation |  | R/A | [8 empty] | R
17 | User story creation | I | R/A | R | R |  |  | R
18 | Use case development |  | R/A |  | C |  |  | C
19 | Validate and obtain approval of requirements | A | R
20 | Requirements prioritization | A | R
21 | Requirements change management | A | R
22 | Facilitating team comprehension of requirements | A | R | I | I | I | I | I | I | I | I | I
23 | Creating recommendations to enhance business processes and product | A | R
24 | Providing user training on product features | A | R
25 | Conducting user research to understand their needs and behavior | A | С | R
26 | Analyzing competitors and the market to identify best practices and trends | A | C | R
27 | Creating user personas and use cases |  | C | R/A | I |  | I |  | I
28 | Creating prototypes and wireframes |  | С | R/A | I |  | I |  | I | I | I
29 | Performing usability tests and analyzin the results | I | I | R/A | I |  | I |  | I
30 | Creating visual concepts and design systems |  |  | R/A
31 | Developing interface mockups based on UI design principles | I | I | R/A | I |  | I |  | I | I | I
32 | Selecting color palettes, typography, and icons |  | C | R/A | C |  |  |  | C | I | I
33 | Creating interactive prototypes | I | C | R/A | C |  |  |  | C | I | I
34 | Design solution presentation and justification | A | C | R
35 | Creating design specifications and style guides | I |  | R/A | I |  |  |  | I | I | I
36 | Maintaining the design system and interface components |  | C | R/A | I |  |  |  | I | I | I
37 | A/B testing | I | I | R/A | I |  |  |  | I
38 | Prioritize and coordinate tasks | R/A |  |  | R |  |  |  |  | R
39 | Technical cross-functional collaboration | A | R | R | R | R | R | R | R | R | R | R
40 | Review сode |  |  |  | A |  | R | I | R
41 | Merge code contributions |  |  |  | A | I | R | R | R | I | I
42 | Ensure code quality and best practices |  |  |  | R/A | I | I | C | I | I | I
43 | Mentor and support team members | A |  |  | R | I | I | R | I |  | R
44 | Manage technical debt and refactoring | I | I |  | R/A | I | I | C | I
45 | Design and implement API endpoints |  |  |  | A | I | R | I | I
46 | Maintaining and scaling databases |  |  |  | A | I | I | R | I | I | I
47 | Designing and optimizing database schemas and models |  |  |  | A | I | I | R | I | I | I
48 | Optimize performance and scalability |  |  |  | A | I | R | R | I
49 | Architect tasks' solutions | I | I |  | A | I | R | R | C
50 | Developing and maintaining APIs for interaction with frontend |  |  |  | A |  | R | C | C
51 | Creating data processing logic for user or external data |  |  |  | A |  | R | R | R
52 | Integrate with 3d-party services |  |  |  | A | I | R | C | I
53 | Implementing user authentication and authorization |  | С |  | A |  | R | R
54 | Protecting data from unauthorized access |  |  |  | A |  | R | R
55 | Unit and integration testing, including test development |  |  |  | A |  | R |  | R
56 | Documenting developed code | I | I |  | A |  | R |  | R | I | I
57 | Documenting APIs and other server-side components | I | I |  | A |  | R |  | I | I | I
58 | Creating and maintaining architectural documentation | I | I |  | A | I | I | R | I
59 | Providing architectural training and mentoring to the team |  |  |  | A | I | I | R | I
60 | Researching and proposing innovative solutions to improve the system | I | I |  | A | I | I | R | I
61 | Creating and maintaining UI components based on libraries |  |  |  | A |  |  |  | R
62 | Using libraries |  |  |  | A |  |  |  | R
63 | Working with frameworks |  |  |  | A |  |  |  | R
64 | Developing interactive elements using JavaScript |  |  |  | A |  |  |  | R
65 | Creating CSS styles to design interface elements |  |  |  | A |  |  |  | R
66 | Writing semantically correct HTML code |  |  |  | A |  |  |  | R
67 | Creating interactive and responsive web pages |  |  |  | A |  |  |  | R
68 | Integrate with backend APIs |  |  |  | A | I | I | I | R
69 | Ensure cross-browser compatibility |  |  |  | A | I | I | I | R
70 | Dev, test and prod environments setup | I |  |  | A | R | I | I | I | I | I
71 | Set up and manage CI/CD pipelines |  |  |  | A | R | I | I | I
72 | Configure and maintain cloud infrastructure |  |  |  | A | R | I | I | I
73 | Implement automated testing and deployment |  |  |  | A | R | I | I | I
74 | Monitor application performance and logs |  |  |  | A | R | I | C | I
75 | Ensure security and compliance of the infrastructure |  |  |  | A | R | I | C | I
76 | Conduct performance and load testing |  |  |  | A | R | I | C | I
77 | Developing and maintaining DevOps infrastructure and process documentation | I |  |  | A | R
78 | Providing consultation on DevOps matters |  |  |  |  | R/A
79 | Develop test plan and strategy | [8 empty] | R/A
80 | Create and execute test cases, scenarios and checklists | [8 empty] | A | R
81 | Perform functional, smoke, crytical pass and regression testing | [8 empty] | A | R
82 | Log and track defects | [8 empty] | A | R
83 | Maintaining test documentation up-to-date | [8 empty] | A | R
84 | Consulting on testing and quality matters | I | I | I | I | I | I | I | I | R/A | I
85 | Preparing test results reports | I | [7 empty] | A | R
86 | Analyzing and optimizing testing process | [8 empty] | R/A | I
87 | Implementing new testing methodologies and tools | I | [7 empty] | R/A | I
88 | Log analysis for error diagnostics and localization |  |  |  | С | С | С | С | С | A | R
89 | L10n, i18n, accessibility, instalation testing | С | С | [6 empty] | A | R
90 | Requirements analysis and testing | I | C | [6 empty] | A | R
91 | Participate in the risk assessment process | A | R | R | R | R | R | R | R | R | R | R
92 | Participate in the estimation process | A | R | R | R | R | I | R | R | R | I | I
93 | Bug fixing and error resolution | I |  |  | A | R | R | R | R | I | I
94 | Evaluating performance and providing feedback to team members | R/A | I | I | R | I | I | I | I | R | I | I
95 | Creating user guides | A | C | C | C |  |  |  | C |  |  | R
96 | Revising existing documents for updates and enhancements | A | C | C | C | C | C | C | C | C | C | R
97 | Analyzing technical information and structuring it to create clear documentation | A | C | C | C | C | C | C | C | C | C | R
98 | Organizing information into a logical structure | A | [9 empty] | R
99 | Analyzing user feedback and communicating it to the team | R/A | R | I | I | I | I | I | I | I | I | R
100 | Implementing new approaches to documentation creation | A | C | [8 empty] | R
101 | Translating documentation into English | I | [9 empty] | R/A
102 | Adapting documentation to cultural specifics | A | [9 empty] | R

## Legend_Darina Ozgun
Legend
Responsible: The person who does the work to achieve the task. They have responsibility for getting the work done or decision made.
Accountable: The person who is accountable for the correct and thorough completion of the task. This is the role that responsible is accountable to and approves their work.
Consulted: The people who provide information for the project and with whom there is two-way communication.
Informed: The people who are kept informed about progress and with whom there is one-way communication. These are people that are affected by the outcome of the tasks so need to be kept up-to-date.